## Sheet1
HREiR Action plan template 2021-2023
Details
| Institution name: | ARU | The institutional audience* for this action plan includes:
| Cohort number: | 8 | Audience | # | Comments
| Date of submission: | 2023-05-19 | Research staff | 59 | 17 Research Assistants; 42 Reseach Fellows
|  |  | Postgraduate researchers | 0
|  |  | Research and teaching staff | 406 | 6 RI staff, 12 Research Managers, 39 Professors; 349 staff on research & teaching contracts
Column1 | Obligation2 | Action | Success Meaure (SMART) | Deadline | Responsibility | Progress upadate (to be completed for submission) | Outcome/result | Column2
| Obligation | Action | Success measure (SMART) | Deadline | Responsibility | Progress update (to be completed for submission) | Outcome/ result
Environment and Culture
Institutions must:
ECI1 | Ensure all relevant staff are aware of the Concordat | 1. We will include information about the Concordat in the Induction checklist for new staff. 2. We will include information about the Concordat in the Research Induction and ensure links to it and the Vitae site about it are included on induction webpages 3. We will highlight the Concordat in newsletters for current staff 4. Once signed, we will email all staff via the VC Newsletter and the staff bulletin. | 1.CEDAR survey shows increased awareness of Concordat from 35% to 45% in 2021 with rising %s in subsequent years 2. Actions 1, 2, 3, 4 promotional activity completed | 1. June 2021; 2. October 2021 3. Sept 2021 4.Sept 2021 | 1. RDM/DDRIs 2.RDM 3. RDM/Chair RDWG 4. RDM/Chair RDWG | 1. CEDARS 2021 showed 42% have some understanding of the Concordat to Support the Career Development of Researchers. Action plan developed for 2023 iteration to promote CEDARS more widely. 2, 3, 4. Actions completed but promotion of awareness of Concordat ongoing because of new staff and need to reach larger audience. | 1-4. No further action-business as usual in ongoing promotion
ECI2 | Ensure that institutional policies and practices relevant to researchers are inclusive, equitable and transparent, and are well-communicated to researchers and their managers | 1. Review and revise our Research Induction 2. Review further and promote Research development opportunities through Research Induction, Faculty newsletters, co-ordination with DDRIs in Faculties and via Researcher Development Newsletter 3. New and newly promoted managers trained on key policies and procedures relating to research staff e.g. fixed term contracts | 1. Induction Reviewed and revised as necessary 2.a Promotion activities completed 2.b. Awareness of Research Development Opportunities in CEDAR Survey increased from 46% to 60%; 3. Of new staff on research and teaching contracts or research only contracts, 75% have attended the research induction within the first 6 months of joining ARU. | 1. Sept 2021 2.a Ongoing 2.b. June 2023 Survey 3. April 2023 | 1. RDM 2a.RDM 2b. RDM/DDsR&I 3. RDM/HR Services/DDsR&I | 1. Research and Innovation Staff Induction (RISI) was launched online in May 2021 and most recently took place in early May 2023. The programme and content is reviewed and updated with each iteration. Moved to face to face delivery from January 2023 and more speed networking events and a networking lunch included. Induction attendance improving but as at 30 April 2023, 139 staff had attended since September 2021, representing 39% of new starters joining ARU. 2a. Researcher development opportunities promoted extensively through monthly newsletters, DDRIs in Faculties, the Research & Innovation Staff Induction and ECR networks in Faculties. 2b. 46% stated they were aware what researcher development opportunities were available. 3. Low uptake by HOS and DHOS to attend training. | 1 No further action- business as usual in ongoing promotion 2. Ongoing - now business as usual. We will keep promotion and monitoring the promotion of researcher development oppertunities. 3. Carried forward
ECI3 | Promote good mental health and wellbeing through, for example, the effective management of workloads and people, and effective policies and practice for tackling discrimination, bullying and harassment, including providing appropriate support for those reporting issues | 1. Review of Annual Workload Balancing Model (AWBM) undertaken 2. Recommendations following completion of AWBM review implemented | 1. Review of AWBM Completed 2. Recommendations implemented in accordance with timescale recommended | 1. Sept 2021 2. As agreed following outcome of review | HR Services & Chair of AWBM Working Group | 1 and 2. CEDARS 2021, focus group feedback and the Staff Survey informed changes in our policy and practice, including systems of appraisal, and the introduction of revised research time allocations in the new AWBM agreement. AWBM was revised and implemented for 2022-23 with enhanced allocations for research, researcher development and ECRs. | 1 and 2. No further action
ECI4 | Ensure that managers of researchers are effectively trained in relation to equality, diversity and including, wellbeing and mental health | 1. Ensure EDI issues completed as compulsory part of probation 2. Work towards achieving the Advance HE Race Equality Charter 3. Make progress towards submission for the Disability Confident Leader status 4. Review the implementation of the Flexible and Agile working policies 5. Health and Wellbeing group proposals developed | 1. Completion of EDI training during probation exceeds 85% of new staff on an annual basis 2. Advance HE Race Equality Charter Award submitted. 3. Progress made in preparation of submission for Disability Confident Leader status. 4. Flexible and Agile Working policies reviewed 5. New Health and Wellbeing group brings forward proposals | 1. Annually in Sept 2. Dec 2022 3. 2027 4. Sept 2022 5. Sept 2021 | 1. HR and line managers 2. EDI Group 3. HR Services 4.HR Services 5. Health and Wellbeing Group | 1. As at July 2022 84% of staff on probation had completed EDI training. 2. Advance HE Race Equality Charter submission made, and Bronze Award received. 3. Disability Confident Leader preparations ongoing 4. Agile working is now a standard expectation across ARU, and our agile and flexible working policies have been incorporated into a single policy which is due for review in May 2024. 5. Health and Wellbeing Group has become the People & Culture Board, reporting to University Executive Team in recognition of the importance of this area of work. Relevant proposals developed and implemented include in-house staff counselling, the introduction of Wellbeing Champions facilitating a variety of activities and workshops, and mental health First Aiders across each campus and in Faculties and Professional Service areas. A new Equality, Diversity and Inclusion offer has also been developed and will be implemented in June 2023. | 1 and 2. No further action. 3. Ongoing 4 and 5. No further action.
ECI5 | Ensure that researchers and their managers are aware of, and act in accordance with, the highest standards of research integrity | 1. Ensure RI training successfully completed as compulsory part of probation 2. RI training promoted to current staff and successful completion monitored 3. Implement actions from the Gap Analysis arising from signing the new Concordat for Research Integerity 4. Monitor research integrity through the annual research activity report to the Board of Governors. | 1. Successful completion of RI training by staff on probation exceeds 90% 2. Successful completion of RI training by current staff exceeds 60% . 3. Actions from Gap Analysis for Concordat implemented 4. Board report completed annually and actions taken forward | 1. Annually in Sept 2. Sept 2022 3. Sept 2022 4. Annually | 1 & 2. HR and line managers 3 Chair RIWG 4. Director RIDO | 1 and 2. Research Integrity training has been reviewed. New 'Quality through Integrity' course being introduced in mid-2023 on a platform that will provide more robust data analysis and monitoring. Completion rates have been increasing. Dec 2022 data shows Faculty-level completion rates of between 50% and 75% overall; among probationary staff, the completion rates were 79% for starters in 2021, and 59% for starters in 2022, this latter figure being affected by the termination of our previous training provision at the end of 2022 and the time left for some 2022 starters to complete probation. Anecdotally, the rise in completion rates is linked to staff on probation as probation cannot be passed without completing this compulsory RI training module, and this is now being more robustly enforced. 3. Research Integrity Gap Analysis completed and action plan being implemented and monitored by RIWG (last update 20 March 2023). Actions include implementing a new RI training platform (to be launched by mid-2023), promoting RI and ethics training at the regular researcher induction events, and providing stand-alone training sessions run through the staff RDP. RIWG was merged with the University Research Ethics Committee in May 2023. The new Ethics & Research Integrity Committee (ERIC) will continue to oversee the Gap Analysis and Action Plan as business as usual. 4. Board report completed on annual basis | 1 and 2. Carried forward 3 and 4. No further action.
ECI6 | Regularly review and report on the quality of the research environment and culture, including seeking feedback from researchers, and use the outcomes to improve institutional practices | 1. Run CEDAR Survey to gain researcher insights 2. Review CEDAR Survey data and devise action plan. 3. Run Postgraduate Researcher Evaluation Survey (PRES) to gain PGR insights 4. Review PRES feedback 5. Use Staff Survey and quarterly Pulse Survey information relating to research to inform development of research environmen and culture 6. Include wide range of staff in development in new R &I Strategy 7. Revitalise Researcher Development Network 8. Initiatie ECR Network | 1. CEDAR Survey run with 50% completion rate 2. CEDAR Survey results reviewed 3. PRES run 4. PRES reviewed 5.a Quarterly Pulse surveys run and results analysed as they pertain to research 5.b Staff survey run and results analysed as it pertains to research 6. Consultation for development of new R&I strategy includes involvement from researchers at all levels and from all faculties 7. Identify staff to lead RDN 8. Identify ECRs to lead on ECR Network | 1. June 2021 2. Oct 2021 3. July 2022 4. Oct 2022 5a. Dec 2021 5b. Dec 2022 6. June 2022 7. Oct 2021 8. Oct 2021 | 1&2) RDM 3&4) ADDS 5a and 5b) HR 6. DvC R&I 7. RDM 8. RDM | 1. CEDARS 2021 complete but only achieved 22% take up. 2. CEDARS 2021 data summarised and reported to RIC. Action plan developed for 2023 iteration to promote CEDARS more widely. Outputs from CEDARS fed directly into the researcher development programme. Key findings were also taken to other programmes including AWBM and Health & Wellbeing to inform their actions and proposals. RDWG used CEDARS data to advise on policy and practice, including induction and support services. 3. and 4. PRES survey run and 35% response rate achieved. Action Plan developed and being implemented with the aim of creating a more positive environment and an inclusive connected community. This includes twice weekly writing sessions, monthly in-person drop in for Doctoral students and supervisors with the Dean of the Doctoral School; use of dedicated PhD physical space; increasing the variety of training available for PGRs, using in-person and online mediums; regular seminars for PGRs and guests to present at; and strengthening relationships between Student Services, Faculties and the Doctoral School. 5. "Pulse" surveys run in January and July 2021 only due to "survey fatigue" concerns. Focus did not pertain to research. New platform for staff surveys introduced in 2022 enabling a more values-based approach, use of emotional analytics etc to give more valuable insights, and review of data as it pertains to research continues. EDI-focussed Pulse Survey launched May 2023. 6. R&I Strategy consultation was university wide, task and finish groups were established for different elements of the strategy and colleagues at all levels were involved. 7. RDN Networks have not been reconvened due to overlap with ECR networks and other initiatives developing from the new R&I Strategy. 8. ECR networks currently led by Deputy Deans but seeking ECR leadership to continue their longevity and expansion | 1-7. No further action. 8. Carried forward.
Funders must:
ECF1 | Including requirements which promote equitable, inclusive and positive research cultures and environments in relevant funding calls, terms and conditions, grant reporting, and policies
ECF2 | Consider how funding opportunities and policies can facilitate different patterns and ways of working, and promote the wellbeing and mental health of researchers
ECF3 | Ensure that funding call requirements and selection processes offer equality of opportunity between different groups of researchers, recognise personal contexts, and promote positive research cultures and working conditions
Managers of researchers must:
ECM1 | Undertake relevant training and development opportunities related to equality, diversity and inclusion, and put this into practice in their work | 1. Annual review of attendance of managers, DHoS, RI Directors, PIs, on EDI Training 2. Implement proposals from new EDI group as work towards Race Equality Charter Award submission 3. Run and promote LGBT intersectionality workshops for staff and review attendance by managers, RI Directors, PIs | 1. Annual review of attendance completed 2. Proposals finalised and Race Equality Charter application submitted 3. LGBT intersectionality workshops delivered and attendance reviewed | 1. Annual 2. Dec 2022 3. Sept 2022 Annual | 1. HR Services and Line Managers 2. Chair EDI Group 3. HR Services | 1. 81% of Managers had completed EDI training as at July 2022 2. Advance HE Race Equality Charter submission made, and Bronze Award received. 3. LGBT Intersectionality workshops slightly delayed but included in 2022/23 staff development programme. | 1-3 No further action.
ECM2 | Ensure that they and their researchers act in accordance with the highest standards of research integrity and professional conduct | 1. Ensure RI training successfully completed by new starters as compulsory part of probation 2. RI training promoted to current staff and successful completion monitored 3. Implement actions from the Gap Analysis arising from signing the new Concordat for Research Integerity 4. Monitor research integrity through the annual research activity report to the Board of Governors. | 1. Successful completion of RI training by staff on probation exceeds 90% 2. Successful completion of RI training by current staff exceeds 60% . 3. Actions from Gap Analysis for Concordat implemented 4. Board report completed annually. | 1. Annually in Sept 2. Sept 2022 3. Sept 2022 4. Annually | 1 & 2. HR and line managers 3 Chair RIWG 4. Director RIDO | 1 and 2. Research Integrity training has been reviewed. New 'Quality through Integrity' course being introduced in mid-2023 on a platform that will provide more robust data analysis and monitoring. Completion rates have been increasing. Dec 2022 data shows Faculty-level completion rates of between 50% and 75% overall; among probationary staff, the completion rates were 79% for starters in 2021, and 59% for starters in 2022, this latter figure being affected by the termination of our previous training provision at the end of 2022 and the time left for some 2022 starters to complete probation. Anecdotally, the rise in completion rates is linked to staff on probation as probation cannot be passed without completing this compulsory RI training module, and this is now being more robustly enforced. 3. Research Integrity Gap Analysis completed and action plan being implemented and monitored by RIWG (last update 20 March 2023). Actions include implementing a new RI training platform (to be launched by mid-2023), promoting RI and ethics training at the regular researcher induction events, and providing stand-alone training sessions run through the staff RDP. RIWG was merged with the University Research Ethics Committee in May 2023. The new Ethics & Research Integrity Committee (ERIC) will continue to oversee the Gap Analysis and Action Plan as business as usual. 4. Board report completed on annual basis | 1 and 2. Carried forward 3 and 4. No further action.
ECM3 | Promote a healthy working environment that supports researchers' wellbeing and mental health, including reporting and addressing incidents of discrimination, bullying and harassment, and poor research integrity | 1. Review of Annual Workload Balancing Model (AWBM) undertaken 2. Recommendations following completion of AWBM review implemented 3. Review the effectiveness of new Health and Wellbeing measures | 1. Review of AWBM Completed 2. AWBM Working Group proposals implemented in accordance with timescale recommended 3. New Health and Wellbeing measures reviewed | 1. Sept 2021 2. As agreed as part of review 3. Sept 2022 | 1.&2. HR Services & Chair of AWBM Working Group 3. HR Services | 1.and 2. AWBM was revised and implemented for 2022-23 with enhanced allocations for research, researcher development and ECRs. 3. Relevant proposals developed and implemented include in-house staff counselling, the introduction of Wellbeing Champions facilitating a variety of activities and workshops, and mental health First Aiders across each campus and in Faculties and Professional Service areas. A new Equality, Diversity and Inclusion offer has also been developed and will be implemented in June 2023. | 1-3. No further action.
ECM4 | Consider fully, in accordance with statutory rights and institutional policies, flexible working requests and other appropriate arrangements to support researchers | 1. Review implementation of new Flexible working policy to ensure they are effectively embedded and implemented 2. . Review implementation of new Agile working policy to ensure they are effectively embedded and implemented | 1. Take up of Flexible working arrangements reviewed 2. Implementation of new Agile Working Policy reviewed | 1. Sept 2022 2. Sept 2022 | 1. HR Services 2. HR Services | 1 and 2. Agile working is now a standard expectation across ARU, and our agile and flexible working policies have been incorporated into a single policy which is due for review in May 2024. | 1 and 2. No further action
ECM5 | Engage with opportunities to contribute to policy development aimed at creating a more positive research environment and culture within their institution | 1. Actively promote CEDAR Survey to staff; 2. Actively promote PGR Survey; 3. Ensure active promotion of opportunity to participate in development of new R&I Strategy 4. Actively promote opportunities to join formal committees, working groups and consultations 5. Invite contributions to University responses to sector consultations and strategies e.g. in KE, Research Integrity, Researcher Development | 1a. CEDARS Survey run with 50% completion rate 1b CEDAR Survey results reviewed 2a. PRES run achieving 50% completion rate 2b. PRES results reviewed 3. Involvement of researchers at all career stages and from all faculties in development of new R&I strategy 4. Opportunities to join formal committees, working groups and consultations actively promoted. 5. Participation in sector consultations and unviersity strategies actively promoted | 1a. June 2021 1b Oct 2021 2a. July 2022 2b.Oct 2022 3. June 2022 4. Ongoing 5. Ongoing | 1 RDM and DDRIs 2. DDS and DDRIs 3. DvC R&I 4. DvC R&I and DDRIs 5. DvC R&I and DDRIs | 1a. CEDARS 2021 complete but only achieved 22% take up. 1b. CEDARS 2021 data summarised and reported to RIC. Action plan developed for 2023 iteration to promote CEDARS more widely. Outputs from CEDARS fed directly into the researcher development programme. Key findings were also taken to other programmes including AWBM and Health & Wellbeing to inform their actions and proposals. RDWG used the CEDARS to advising on policy and practice, including induction and support services. 2a. and 2b. PRES survey run and 35% response rate achieved. Action Plan developed and being implemented with the aim of creating a more positive environment and an inclusive connected community. This includes twice weekly writing sessions, monthly in-person drop in for Doctoral students and supervisors with the Dean of the Doctoral School; use of dedicated PhD physical space; increasing the variety of training available for PGRs, using in-person and online mediums; regular seminars for PGRs and guests to present at; and strengthening relationships between Student Services, Faculties and the Doctoral School. 3. R&I Strategy consultation was university wide, task and finish groups were established for different elements of the strategy and colleagues at all levels were involved. 4. ECRs formally added to a number of committees and working groups. 5. Consultations and University Strategies actively promoted to staff. | 1-5. No further action.
Researchers must:
ECR1 | Actively contribute to the development and maintenance of a supportive, fair and inclusive research culture and be a supportive colleague, particularly to newer researchers and students | 1. Promote participation in CEDAR Survey 2. Promote participation in PGR Survey 3. Promote opportunities to participate in development of new R&I Strategy 4. Promote opportunities to participate in formal committees, working groups and consultations 5.Promote opportunities to contribute to sector consultations and strategies e.g. in KE, Research Integrity, Researcher Development | 1. CEDAR Survey achieves 50% completion rate 2. PRES achieves 50% completion rate 3. Researchers at all career stages and from all faculties participate in development of new R&I strategy 4. Formal committees, working groups and consultations have representation from across the researcher cohort 5. University responses to sector consultations include input from researchers | 1. June 2021 2. July 2022 3. June 2022 4. Ongoing and annual 5.Ongoing | 1. RDM and DDRIs 2. DDS and DDRIs 3.DvC R&I 4.Chair RDWG 5. DvC R&I, DDsR&I | 1. CEDARS 2021 complete but only achieved 22% take up. 2. PRES survey complete but only achieved 35% response rate. 3. R&I Strategy complete and involved colleagues at all career stages 4. ECRs formally added to a number of committees and working groups. 5. Consultations and University Strategies actively promoted to staff. | 1-5. No further action.
ECR2 | Ensure they act in accordance with employer and funder policies related to research integrity, and equality, diversity and inclusion | 1. Promote completion of RI training as compulsory part of probation 2. Promote completion of training to current staff members 3. Implement actions arising from the Gap Analysis from signing the new Concordat for Research Integerity | 1. Successful completion of RI training by staff on probation exceeds 90% 2. Successful completion of RI training by current staff exceeds 60% 3. Actions from Gap Analysis for Concordat for RI completed | 1. Annually in Sept 2. Sept 2022 3. Sept 2022 | 1 & 2. HR and line managers 3. Chair RIWG | 1 and 2. Research Integrity training has been reviewed. New 'Quality through Integrity' course being introduced in mid-2023 on a platform that will provide more robust data analysis and monitoring. Completion rates have been increasing. Dec 2022 data shows Faculty-level completion rates of between 50% and 75% overall; among probationary staff, the completion rates were 79% for starters in 2021, and 59% for starters in 2022, this latter figure being affected by the termination of our previous training provision at the end of 2022 and the time left for some 2022 starters to complete probation. Anecdotally, the rise in completion rates is linked to staff on probation as probation cannot be passed without completing this compulsory RI training module, and this is now being more robustly enforced. 3. Research Integrity Gap Analysis completed and action plan being implemented and monitored by RIWG (last update 20 March 2023). Actions include implementing a new RI training platform (to be launched by mid-2023), promoting RI and ethics training at the regular researcher induction events, and providing stand-alone training sessions run through the staff RDP. RIWG was merged with the University Research Ethics Committee in May 2023. The new Ethics & Research Integrity Committee (ERIC) will continue to oversee the Gap Analysis and Action Plan as business as usual | 1 and 2. Carried forward 3. No further action.
ECR3 | Take positive action towards maintaining their wellbeing and mental health | 1.Review of AWBM setting process completed 2. Implement recommendations of review of AWBM by Working Group 3. Effectiveness of new Health and Wellbeing measures introduced in 2020-21 reviewed 4.Staff Survey and quarterly Pulse Surveys undertaken | 1. AWBM Reviewed 2. AWBM Working Group proposals implemented 3. New Health and Wellbeing measures reviewed 4. a Quarterly Pulse surveys run and results analysed as they pertain to research 4 b Staff survey run and results analysed as it pertains to research | 1. Sept 2022 2. Sept 2022 3. Sept 2022 4.a Dec 2021 4.b Dec 2022 | 1.&2.Chair AWBM WG & HR Services 3. HR Services 4a and 4b. HR Services | 1.and 2. AWBM was revised and implemented for 2022-23 with enhanced allocations for research, researcher development and ECRs. 3. Relevant proposals developed and implemented include in-house staff counselling, the introduction of Wellbeing Champions facilitating a variety of activities and workshops, and mental health First Aiders across each campus and in Faculties and Professional Service areas. A new Equality, Diversity and Inclusion offer has also been developed and will be implemented in June 2023. 4a and b. "Pulse" surveys run in January and July 2021 only due to "survey fatigue" concerns. New platform for staff surveys introduced in 2022 and full Staff Survey run. | 1-4. No further action.
ECR4 | Use available mechanisms to report staff who fail to meet the expected standards of behaviour, particularly in relation to discrimination, harassment, bullying, and research misconduct | 1. Annual report on incidents of discrimination, bullying and harassment and grievances and complaints 2. Annual report on incidents of academic misconduct 3. Actively promote awareness of current policies and procedures in relation to discrimination, harassment, bullying and research misconduct | 1. Report on incidents of discrimination, bullying and harassment, grievances and complaints completed annually 2. Report on incidents of academic misconduct | 1 & 2 Annually | 1. HR Services 2. Director RIDO | 1 and 2 Reports on bullying and misconduct completed annually and reported to relevannt committees and management groups. | 1-2. No further action - business as usual.
ECR5 | Consider opportunities to contribute to policy development aimed at creating a more positive research environment and culture within their institution | 1. Actively promote CEDAR Survey to staff; 2. Actively promote PGR Survey; 3. Ensure active promotion of opportunity to participate in development of new R&I Strategy 4. Actively promote opportunities to join formal committees, working groups and consultations 5. Invite contributions to University responses to sector consultations and strategies e.g. in KE, Research Integrity, Researcher Development | 1a. CEDARS Survey run with 50% completion rate 1b CEDAR Survey results reviewed 2a. PRES run achieving 50% completion rate 2b. PRES results reviewed 3. Involvement of researchers at all career stages and from all faculties in development of new R&I strategy 4. Opportunities to join formal committees, working groups and consultations actively promoted. 5. Participation in sector consultations and university strategies actively promoted | 1a. June 2021 1b Oct 2021 2a. July 2022 2b.Oct 2022 3. June 2022 4. Ongoing 5. Ongoing | 1 RDM and DDRIs 2. DDS and DDRIs 3. DvC R&I 4. DvC R&I and DDRIs 5. DvC R&I and DDRIs | 1a. CEDARS 2021 complete but only achieved 22% take up. 1b. CEDARS 2021 data summarised and reported to RIC. Action plan developed for 2023 iteration to promote CEDARS more widely. Outputs from CEDARS fed directly into the researcher development programme. Key findings were also taken to other programmes including AWBM and Health & Wellbeing to inform their actions and proposals. RDWG used the CEDARS to advising on policy and practice, including induction and support services. 2a. and 2b. PRES survey run and 35% response rate achieved. Action Plan developed and being implemented with the aim of creating a more positive environment and an inclusive connected community. This includes twice weekly writing sessions, monthly in-person drop in for Doctoral students and supervisors with the Dean of the Doctoral School; use of dedicated PhD physical space; increasing the variety of training available for PGRs, using in-person and online mediums; regular seminars for PGRs and guests to present at; and strengthening relationships between Student Services, Faculties and the Doctoral School. 3. R&I Strategy consultation was university wide, task and finish groups were established for different elements of the strategy and colleagues at all levels were involved. 4. ECRs formally added to a number of committees and working groups. 5. Consultations and University Strategies actively promoted to staff. | 1-5 No further action.
Employment
Institutions must:
EI1 | Ensure open, transparent and merit-based recruitment, which attracts excellent researchers, using fair and inclusive selection and appointment practices | 1. Review recruitment processes | 1. Review of recruitment practices completed | 1. June 2022 | 1. HR Services | 1. Review completed | 1. No further action.
EI2 | Provide an effective induction, ensuring that researchers are integrated into the community and are aware of policies and practices relevant to their position | 1. Review research induction and consider whether to make it compulsory. 2. Actively promote research induction | 1a. Research induction review completed 1b. Review particpants' feedback from inductions 2. 80% of new staff attend Research Induction within 6 months of joining | 1 & 2. Sept 2021 3. June 2022 | 1. RDM 2. RDM 3. RDM &DDsRI | 1a Research & Innovation Staff Induction reviewed and constantly updated with each iteration following feedback from participants. 1b. Feedback from inductions is reviewed following every session. It has been very positive with staff feeling that it gives them a great introduction to who is who in the research space and how they can be supported. The networking opportunites have also been described as a highlight of the induction. We are further reviewing the format and frequency of RISI ahead of further iterations in autumn 2023. 2. 139 staff have attended Research & Innovation Staff Induction since September 2021, representing 32% of new starters (data correct at 30 April 2023). The majority of staff at ARU are on teaching and research contracts so may not have time in the first 6 months to attend due to teaching commitments, especially if this was the primary justification for their role. We have previous inductions recorded online for staff to view at any time. | 1. No further action 2. Carried forward.
EI3 | Provide clear and transparent merit-based recognition, reward and promotion pathways that recognise the full range of researchers' contributions and the diversity of personal circumstances | 1. Review implementation of new Academic Career Framework 2. Review career pathways data for Research Fellow, SRF, PRF and develop Academic Framework for these job roles 3. Review promotions data in terms of EDI | 1. New Academic Career Framework reviewed 2. Career pathways reviewed for RF, SRF, PRF roles and Academic Framework developed for these roles 3. Promotions data to be reviewed in relation to EDI | 1. Sept 2021 2. Sept 2022 3. Annually | 1. DvC R&I 2. DvC R&I 3. HR Services | 1. New Academic Framework reviewed and minor changes made. 2. Academic Career Framework has aligned promotions pathways for Research Fellow, Senior and Principal Research Fellow roles to Lecturer, Senior Lecturer and Associate Professor. 3. Promotions data in relation to EDI reviewed. | 1-3. No further action.
EI4 | Provide effective line and project management training opportunities for managers of researchers, heads of department and equivalent | 1. Review content of research/staff development programme in relation to staff and project management 2. Ensure PI and Co-Is of bids have training and development on project management available 3. Through review of appraisal identify colleagues with management training requriements | 1. Research/Staff training and project management training opportunities reviewed 2a. Establish PI and Co-Is staff and project management training requirements 2b. Provide staff and project management training for PIs and Co-Is 3. Review of appraisals completed | 1. Sept 2021 2a. Apr 2022 2b. Apr 2023 3. Oct 2021 and annually | 1. RDM/HR Services 2a. RIDO Post Award/DDsR&I 2b. RIDO Post Award/DDsR&I 3. HRServices/DDsR&I | 1. Review undertaken and gap in area of project management support identified. 2a and 2b. Funding from Research England has been used to purchase a 1-day project management training by Scriptoria, for up to 16 PIs and Co-Is identified by the RIDO Post-Award Team from grants data. Review of feedback from this course, and more detailed analysis of the needs of this group of staff, will be carried forward to inform project management content in the 2023-24 Researcher Development Programme. 3. A new appraisal system - PCDR - introduced in April 2023 which will enable more effective training needs analysis to take place. | 1.No further action. 2 and 3. Carried forward.
EI5 | Ensure that excellent people management is championed throughout the organisation and embedded in institutional culture, through annual appraisals, transparent promotion criteria, and workload allocation | 1. Complete Review of AWBM 2. Implement actions from AWBM review 3. Complete Review of Appraisal system 4. Implement findings of Appraisal System Review 5. Review implementation of new Academic Career Framework 6. Review career pathways data for Research Fellow, SRF, PRF and develop Academic Framework for these job roles | 1. Review of AWBM completed 2. AWBM Working Group proposals implemented 3. Review of Appraisal system completed 4. Actions from Appraisal System review implemented 5. Academic Career Framework reviewed 6. Career pathways for RFs, SRFs, PRFs in Academic Career Framework implemented | 1. Sept 2021 2. As agreed following outcome of review 3. Sept 2021 4. As agreed following outcome of review 5. Sept 2021 6. Sept 2022 | 1&2) Chair AWBM WG & HR Services 3&4) HR Services 5&6) DvC R&I & HRServices | 1 and 2. AWBM system revised and changes implemented for 2022-23 3 and 4. Appraisal system reviewed and a new system, PCDR, implemented in April 2023. 5 and 6. Academic Career Framework review aligned promotions pathways for Research Fellow, Senior and Principal Research Fellow roles to Lecturer, Senior Lecturer and Associate Professor. | 1-6. No further action.
EI6 | Seek to improve job security for researchers, for example through more effective redeployment processes and greater use of open-ended contracts, and report on progress | 1. Establish baseline of % of research staff on fixed term contracts and % who have moved to open-ended contracts 2. Report on progress on reducing research staff on fixed term contracts. | 1. Baseline of % of research staff on fixed term contracts and % moved to open-ended contracts established. 2. Report on reducing research staff on fixed-term contracts completed | 1.Sept 2021 2. June 2022 | 1. HR Services 2. HR Services | 1 and 2. Baseline has been established: as at 31 July 2020, with 61% (n=39) of research-only staff were employed on fixed term contracts. At 31 July 2021 this was 62% (n=41) and at 31 July 2022, 65% (n=56). However, in 2020-21 7.7% of fixed term staff moved to permanent reserach contracts, and in 2022, 14.6%. The aspiration to reduce the number of research staff on fixed term contracts must be set against institutional aspirations to grow external research income, which is likely to mean an increase in fixed term contracts. | 1 and 2. No further action.
EI7 | Consider researchers and their managers as key stakeholders within the institution and provide them with formal opportunities to engage with relevant organisational policy and decision-making | 1. Actively promote CEDAR Survey to staff; 2. Actively promote PGR Survey; 3. Ensure active promotion of opportunity to participate in development of new R&I Strategy 4. Actively promote opportunities to join formal committees, working groups and consultations 5. Invite contributions to University responses to sector consultations and strategies e.g. in KE, Research Integrity, Researcher Development 6. Ensure actions from review of ECR involvement in Committee structure are implemented. | 1a. CEDARS Survey run with 50% completion rate 1b CEDAR Survey results reviewed 2a. PRES run achieving 50% completion rate 2b. PRES results reviewed 3. Involvement of researchers at all career stages and from all faculties in development of new R&I strategy 4. Opportunities to join formal committees, working groups and consultations actively promoted. 5. Participation in sector consultations and university strategies actively promoted 6. Recommendations of changes to committee structure implemented. | 1a. June 2021 1b Oct 2021 2a. July 2022 2b.Oct 2022 3. June 2022 4. Ongoing 5. Ongoing 6. Sept 2022 | 1. RDM & DDsRI 2. DDS & DDsRI 3. DvC R&I 4. DvC R&I and DDsRI 5.DvC R&I and DDsRI 6.Chair RDWG | 1a. CEDARS 2021 complete but only achieved 22% take up. 1b. CEDARS 2021 data summarised and reported to RIC. Action plan developed for 2023 iteration to promote CEDARS more widely. Outputs from CEDARS fed directly into the researcher development programme. Key findings were also taken to other programmes including AWBM and Health & Wellbeing to inform their actions and proposals. RDWG used the CEDARS to advising on policy and practice, including induction and support services. 2a. and 2b. PRES survey run and 35% response rate achieved. Action Plan developed and being implemented with the aim of creating a more positive environment and an inclusive connected community. This includes twice weekly writing sessions, monthly in-person drop in for Doctoral students and supervisors with the Dean of the Doctoral School; use of dedicated PhD physical space; increasing the variety of training available for PGRs, using in-person and online mediums; regular seminars for PGRs and guests to present at; and strengthening relationships between Student Services, Faculties and the Doctoral School. 3. R&I Strategy consultation was university wide, task and finish groups were established for different elements of the strategy and colleagues at all levels were involved. 4. ECRs formally added to a number of committees and working groups. 5. Consultations and University Strategies actively promoted to staff. 6. Changes to committee structures implemented. | 1-6. No further action.
Funders must:
EF1 | Include requirements which support the improvement of working conditions for researchers, in relevant funding calls, terms and conditions, grant reporting, and policies
EF2 | Review the impact of relevant funding call requirements on researchers' employment, particularly in relation to career progression and lack of job security
EF3 | Support institutions to develop policies and frameworks to promote sustainable employment arrangements and enhance job security, and provide opportunities for career progression
EF4 | Consider the balance of their relevant funding streams in providing access to research funding and its impact at all career levels
Managers of researchers must:
EM1 | Undertake relevant training and development opportunities so that they can manage researchers effectively and fulfil their duty of care | 1. Monitor and report on training and development take up by managers of researchers through Research Development Programme and HR run staff development programmes 2. Monitor take up of Research Leaders training and development | 1. Annual review of take up of RDP and HR run staff development sessions by research managers. 2. Annual review of take up of Research Leaders training and development | 1&2 Annual in October | 1. RDM & HR Services 2 RDM | 1. Review of take up of RDP and HR staff development ongoing. 2. Vitae provided a generic research leadership training in December 2022 and January 2023, with a "train the trainer" add-on, reaching more than 70 staff at a variety of career stages across ARU. Working with the "train the trainer" cohort to revise the content to better meet ARU staff needs. | 1. Carried forward. 2. No further action.
EM2 | Familiarise themselves, and work in accordance with, relevant employment legislation and codes of practice, institutional policies, and the terms and conditions of grant funding | 1. Ensure RDP includes training on grant funding and its commitments 2. Record engagement of staff with training and development opportunities in relation to HR issues 3. RIDO post-award team to develop guidance on ensuring compliance with grant funding conditions | 1. Researcher Development Programme includes training on grant funding and its commitments. 2. Staff engagement with training and development in HR issues reviewed 3. Guidance developed | 1. June 2022 2. Annual in October 3. June 2022 | 1. RDM 2. RDM and HR Services 3. RIDO Post Award | 1. RDP developed and reviewed annually and includes training on grant funding. Each Faculty has nominated Research Funding Managers who offer 1-2-1 bespoke support and development to staff preparing grant bids. 2. Review complete and has become business as usual 3. Changes in post-award staff mean this action carried forward. | 1 and 2. No further action 3. Carried forward.
EM3 | Commit to, and evidence, the inclusive, equitable and transparent recruitment, promotion and reward of researchers | 1. Review recruitment processes 2. Review implementation of new Academic Career Framework 3. Review career pathways for Research Fellow, SRF, PRF and develop Academic Framework for these job roles | 1. Review of recruitment processes completed 2. Review of new Academic Career Framework completed 3. Career pathways for RFs, SRFs, & PRFs, implemented Academic Career Framework | 1. June 2022 2. Sept 2021 3. Sept 2022 | 1. HR Services 2 & 3) DvC R&I | 1. Review completed 2. Review completed and minor changes made 3. Academic Career Framework has aligned promotions pathways for Research Fellow, Senior and Principal Research Fellow roles to Lecturer, Senior Lecturer and Associate Professor. | 1-3. No further action
EM4 | Actively engage in regular constructive performance management with their researchers | 1. Review Appraisal System 2. Implement actions from review of Appraisal System 3. Review IRR 4. Implement actions from review of IRR 5. Monitor completion of Appraisls and IRRs and establish baselines for completion rates | 1. Appraisal system review completed 2. Actions from Appraisal System review implemented 3. IRR review completed 4. Actions from IRR review implemented 5. Baseline for appraisal and IRR completion rates established | 1. Sept 2021 2. As agreed following outcome of review 3. Sept 2021 4. As agreed following outcome of review 5. Sept 2022 | 1-5) HR Services | 1 and 2. Appraisal system reviewed and new system - PCDR - introduced in April 2023. 3 and 4. IRR reviewed and augmented to become IRKEP - more explicitly recognising knowledge exchange activities alongside research and reframing the document as a forward-looking plan rather than a backward-facing review. 5. IRKEP process does not allow for systemic monitoring which would provide baselines. IRKEP itself is now robustly tied into AWBM allocation processes, and promoted widely e.g. included in HR new starters checklists to prompt managers' discussions with new staff, the research induction and also through CEDARS (in institutional specific questions). Monitoring IRKEP more directly may be revisited if an alternate approach to provisioning IRKEP is introduced. | 1-5. No further action.
EM5 | Engage with opportunities to contribute to relevant policy development within their institution | 1. Encourage participation rates by managers in consultations e.g. development of new R&I Strategy 2. Promote opportunities for engagement in sector consultations on in KE, Research Integrity, Researcher Development 3.Actively promote opportunities to join formal committees, working groups and consultations | 1. Involvement of researchers at all career stages and from all faculties in development of new R&I strategy 2. Participation in sector consultations and university strategies actively promoted 3. Opportunities to join formal committees, working groups and consultations actively promoted | 1. June 2022 2. Ongoing 3. Ongoing | 1, 2 & 3. DvC R&I and DDRIs | 1. New University Strategies developed and widely consulted on. 2 and 3). Now normal practice | 1-3. No further action
Researchers must:
ER1 | Ensure that they work in accordance with, institutional policies, procedures and employment legislation, as well as the requirements of their funder | 1. Ensure RDP includes training on grant funding and its commitments 2. Record engagement of staff with training and development opportunties in relation to HR issues 3. RIDO post-award team to develop guidance on ensuring compliance with grant funding conditions | 1. Researcher Development Programme includes training on grant funding and its commitments. 2. Staff engagement with training and development in HR issues reviewed 3. Guidance developed | 1. June 2022 2. Annual in October 3. June 2022 | 1. RDM 2. RDM and HR Services 3. RIDO Post Award | 1. RDP developed and reviewed annually and includes training on grant funding. Each Faculty has nominated Research Funding Managers who offer 1-2-1 bespoke support and development to staff preparing grant bids. 2. Review complete and has become business as usual 3. Changes in post-award staff mean this action carried forward. | 1 and 2. No further action 3. Carried forward.
ER2 | Understand their reporting obligations and responsibilities | 1. Research Office (RIDO) and post-award team work closely with researchers to ensure obligations are fulfilled. | 1. 100% of grant awards meet reporting requirements | 1. May 2023 | 1 RIDO Post Award and DDS R&I | 1. No monitoring yet implemented | 1. Carried forward
ER3 | Positively engage with performance management discussions and reviews with their managers | 1. Review Appraisal System 2. Implement actions from review of Appraisal System 3. Review IRR 4. Implement actions from review of IRR 5. Monitor completion of Appraisals and IRRs and establish baselines for completion rates | 1. Appraisal system review completed 2. Actions from Appraisal System review implemented 3. IRR review completed 4. Actions from IRR review implemented 5. Baseline for appraisal and IRR completion rates established | 1. Sept 2021 2. As agreed following outcome of review 3. Sept 2021 4. As agreed following outcome of review 5. Sept 2022 | 1-5) HR Services | 1 and 2. Appraisal system reviewed and new system - PCDR - introduced in April 2023. 3 and 4. IRR reviewed and augmented to become IRKEP - more explicitly recognising knowledge exchange activities alongside research and reframing the document as a forward-looking plan rather than a backward-facing review. 5. IRKEP process does not allow for systemic monitoring which would provide baselines. IRKEP itself is now robustly tied into AWBM allocation processes, and promoted widely e.g. included in HR new starters checklists to prompt managers' discussions with new staff, the research induction and also through CEDARS (in institutional specific questions). Monitoring IRKEP more directly may be revisited if an alternate approach to provisioning IRKEP is introduced. | 1-5. No further action.
ER4 | Recognise and act on their role as key stakeholders within their institution and the wider academic community | 1. Actively promote CEDAR Survey to staff; 2. Actively promote PGR Survey; 3. Ensure active promotion of opportunity to participate in development of new R&I Strategy 4. Actively promote opportunities to join formal committees, working groups and consultations 5. Invite contributions to University responses to sector consultations and strategies e.g. in KE, Research Integrity, Researcher Development 6. Ensure actions from review of ECR involvement in Committee structure are implemented. | 1a. CEDARS Survey run with 50% completion rate 1b CEDAR Survey results reviewed 2a. PRES run achieving 50% completion rate 2b. PRES results reviewed 3. Involvement of researchers at all career stages and from all faculties in development of new R&I strategy 4. Opportunities to join formal committees, working groups and consultations actively promoted. 5. Participation in sector consultations and university strategies actively promoted 6. Recommendations of changes to committee structure implemented. | 1a. June 2021 1b Oct 2021 2a. July 2022 2b.Oct 2022 3. June 2022 4. Ongoing 5. Ongoing 6. Sept 2022 | 1. RDM & DDsRI 2. DDS & DDsRI 3. DvC R&I 4. DvC R&I and DDsRI 5.DvC R&I and DDsRI 6.Chair RDWG | 1a. CEDARS complete but only achieved 22% take up. 1b. CEDARS data summarised and reported to RIC. Action plan developed for 2023 iteration to promote CEDARS more widely. Outputs from CEDARS fed directly into the researcher development programme. Key findings were also taken to other programmes including AWBM and Health & Wellbeing to inform their actions and proposals. RDWG used the CEDARS to advising on policy and practice, including induction and support services. 2a. and 2b. PRES survey run and 35% response rate achieved. Action Plan developed and being implemented with the aim of creating a more positive environment and an inclusive connected community. This includes twice weekly writing sessions, monthly in-person drop in for Doctoral students and supervisors with the Dean of the Doctoral School; use of dedicated PhD physical space; increasing the variety of training available for PGRs, using in-person and online mediums; regular seminars for PGRs and guests to present at; and strengthening relationships between Student Services, Faculties and the Doctoral School. 3. R&I Strategy consultation was university wide, task and finish groups were established for different elements of the strategy and colleagues at all levels were involved. 4. ECRs formally added to a number of committees and working groups. 5. Consultations and University Strategies actively promoted to staff. 6. Changes to committee structures implemented. | 1-6 No further action.
Professional and Career Development
Institutions must:
PCDI1 | Provide opportunities, structured support, encouragement and time for researchers to engage in a minimum of 10 days professional development pro rata per year, recognising that researchers will pursue careers across a wide range of employment sectors | 1. Ensure line managers have good understanding of Concordat and the defintion of researcher and of development being used by ARU for implementation of Concordat 2.Clarify how 10 days time is included in AWBM allocation. 3. Promote clear understanding that staff development of researchers is not just research specific and can take many forms including opportunities beyond the programme itself and responsive to staff IRRs | 1a. CEDAR survey shows increased awareness of Concordat from 35% to 45% in 2021 with rising %s in subsequent years 1b. Awareness of Research Development Opportunities in CEDAR Survey increased from 48% to 60% by 2023; 2. 50% of staff included by Concordat definition achieving 10 days development 3. Training opportunities relevant to Researcher Development, provided by faculties and HR training progammes to supplement Researcher Development Programme | 1a. June 2021 1b. June 2023 2. Sept 2023 3. Sept 2022 | 1a. RDM & DDsR&I 1b. RDM & DDsR&I 2. RDM DDsR&I/Chair RDWG 3. RDM, HR Services, DDsR&I | 1a. CEDARS 2021 showed 42% have some understanding of the Concordat to Support the Career Development of Researchers. Outcomes of CEDARS 2023 in this respect awaited. 1b. CEDARS 2021 data showed 69% (n=74) had engaged in or attended activities provided through ARU’s Staff Researcher Development Programme (53% in CEDARS 2020). 83% (n=89) stated they received the monthly Staff Researcher Development newsletter. 2.CEDARS 2021 showed 64% of respondents (n=109) spent up to four days on researcher development in the last year and 16% of respondents spent ten days on training and professional development activities in the last year, Further understanding of what constitutes training and development needs to be further promoted. Significant change made to AWBM to include 100 credits (=100 hours) for full time staff for researcher development, available for all research active staff subject to line management approval; 3. Faculties provide formal and informal training and development programmes. Ongoing liaison with HR services about their provision and opportunities for research focus in training and development sessions. | 1-3. No further action - now business as usual
PCDI2 | Provide training, structured support, and time for managers to engage in meaningful career development reviews with their researchers | 1. Review Appraisal System 2. Implement actions from review of Appraisal System 3. Review IRR 4. Implement actions from review of IRR 5. Review AWBM 6. Implement actions from AWBM review | 1. Appraisal system review completed 2. Actions from Appraisal System review implemented 3. IRR review completed 4. Actions from IRR review implemented 5. AWBM review completed 6. AWBM review actions implemented | 1. Sept 2021 2. As agreed following outcome of review 3. Sept 2021 4. As agreed following outcome of review 5. Sept 2021 6. As agreed following outcome of review | 1-6. HR Services | 1 and 2. Appraisal system reviewed and new system - PCDR - introduced in April 2023. 3 and 4. IRR reviewed and augmented to become IRKEP - more explicitly recognising knowledge exchange activities alongside research and reframing the document as a forward-looking plan rather than a backward-facing review. 5. IRKEP process does not allow for systemic monitoring which would provide baselines. IRKEP itself is now robustly tied into AWBM allocation processes, and promoted widely e.g. included in HR new starters checklists to prompt managers' discussions with new staff, the research induction and also through CEDARS (in institutional specific questions). Monitoring IRKEP more directly may be revisited if an alternate approach to provisioning IRKEP is introduced. | 1-5. No further action.
PCDI3 | Ensure that researchers have access to professional advice on career management, across a breadth of careers | 1. Make visiting role appointments to support sector awareness beyond academia so that all Research Institutes and Faculties have visiting appointees. 2. Review pilot ECR mentoring scheme and for effectiveness of career advice | 1. Broad base of expertise available to researchers through visiting appointees 2. ECR Mentoring scheme reviewed in terms of effectiveness of career advice | 1. Sept 2022 2. Nov 2021 | 1. DDsR&I /RIDO 2. RDMI | 1. Faculties increasing number of visiting appointees. 2. ECR Mentoring scheme and mentoring scheme more widely being reviewed across ARU; much research mentoring happens informally and formally across faculties in any case. | 1. No further action - now business as usual. 2. Carried forward.
PCDI4 | Provide researchers with opportunities, and time, to develop their research identity and broader leadership skills | 1. Review ECR mentoring programme and evalute whether to introduce across university 2. Review definition of research leaders and identify expectations of colleagues in those roles and how we support and develop them 3. Review AWBM 4. Review IRR 5. Review appraisal system 6. Develop support for mid careers researchers and help transitions from ECR status | 1. Mentoring scheme pilot reviewed and considered as to whether to introduce it across university 2. Research leadership roles identified and expectations articulated recognising different aspects of research role and different degrees of workload allocated to research 3. AWBM Review completed 4. IRR review completed 5. Appraisal system review completed 6. Identify needs of mid-career staff and develop training as part of researcher development programme | 1. Nov 2021 2. Sept 2021 3. Sept 2021 4. Sept 2021 5. Sept 2021 6. Nov 2021 | 1. RDM 2. Chair RDWG/ RDM 3. Chair AWBM WG 4&5. HR Services 6. RDM/DDsR&I | 1. ECR Mentoring scheme and mentoring scheme more widely being reviewed across ARU; much research mentoring happens informally and formally across faculties in any case. 2. Vitae provided a generic research leadership training in December 2022 and January 2023, with a "train the trainer" add-on, reaching more than 70 staff at a variety of career stages across ARU. Working with the "train the trainer" cohort to revise the content to better meet ARU staff needs. 3. AWBM was revised and implemented for 2022-23 with enhanced allocations for research, researcher development and ECRs. 4. IRR reviewed and augmented to become IRKEP - more explicitly recognising knowledge exchange activities alongside research and reframing the document as a forward-looking plan rather than a backward-facing review. 5. Appraisal system reviewed and new system - PCDR - introduced in April 2023. 6. Mid career researcher training needs being identified and relevant training developed | 1 and 2. Carried forward 3-6. No further action
PCDI5 | Recognise that moving between, and working across, employment sectors can bring benefits to research and researchers, and support opportunities for researchers to experience this | 1. Increase training and development delivered by those in and from sectors beyond academia 2. Increase number of compacts with employers 3. Increase collaborative working with employers e.g. KTPs, KEEP+ and consultancy | 1. Training and development delivered by those in and from sectors beyond academia increased. 2. Number of university compacts with employers increased 3. Number of KTPs and consultancy projects increased from 2021 baseline. | 1. Sept 2022 2. Sept 2022 3. May 2023 | 1. RDM& DDsR&I 2. DDsR&I, DvC R&I 3. DDsR&I, RIDO | 1. Training delivered by wide range of external experts e.g. in media and industry 2. Number of compacts increased strengthening ties with industry and exceeded university KPI 3. Number of KTP projects not yet increased. All external income generation activities, including research grant bidding, consultancy and contract activity, and KTPs are subject to quarterly External Income Review meetings at Faculty level. | 1-2. No further action 3. Carried forward.
PCDI6 | Monitor, and report on, the engagement of researchers and their managers with professional development activities, and researcher career development reviews | 1. Monitor and report on training and development take up by researchers and managers of researchers through Research Development Programme and HR run staff development programmes 2. Monitor and report on take up of Research Leaders training and development 3. Review Appraisal System 4. Implement actions from review of Appraisal System 5. Review IRR 6. Implement actions from review of IRR 7. Monitor completion of Appraisals and IRRs and establish baselines for completion rates | 1. Annual report on take up of research training and development 2. Annual report on take up of research leadership training and development 3. Review of Appraisal completed 4. Appraisal Working Group proposals implemented 5. Review of IRR completed 6. Actions from IRR review implemented 7. Baseline for appraisal and IRR completion rates established | 1 & 2. Annually in October 3.Sept 2021 4. As agreed following outcome of review 5. Sept 2021 6. As agreed following outcome of review 7. Sept 2022 | 1 & 2. RDM & HR Services 3-7 HR Services | 1. RDP reviewed annually including alignment with HR provision, and is now business as usual. 2. Vitae provided a generic research leadership training in December 2022 and January 2023, with a "train the trainer" add-on, reaching more than 70 staff at a variety of career stages across ARU. Working with the "train the trainer" cohort to revise the content to better meet ARU staff needs. 3 and 4. Appraisal system reviewed and new system - PCDR - introduced in April 2023. 5 and 6. IRR reviewed and augmented to become IRKEP - more explicitly recognising knowledge exchange activities alongside research and reframing the document as a forward-looking plan rather than a backward-facing review. 7. New PCDR system will allow monitoring of take-up. IRKEP process does not allow for systemic monitoring which would provide baselines. IRKEP itself is now robustly tied into AWBM allocation processes, and promoted widely e.g. included in HR new starters checklists to prompt managers' discussions with new staff, the research induction and also through CEDARS (in institutional specific questions). Monitoring IRKEP more directly may be revisited if an alternate approach to provisioning IRKEP is introduced. | 1-6. No further action 7. Carried forward.
Funders must:
PCDF1 | Incorporate specific professional development requirements in relevant funding calls, terms and conditions, grant reporting, and policies. This should include researchers' engagement in a minimum of 10 days' professional development pro rata per year, and evidence of effective career development planning
PCDF2 | Embed the Concordat Principles and researcher development into research assessment strategies and processes
PCDF3 | Acknowledge that a large proportion of the researchers they fund will move on to careers beyond academia, and consider how they can encourage and support this within their remit
Managers of researchers must:
PCDM1 | Engage in regular career development discussions with their researchers, including holding a career development review at least annually | 1. Review Appraisal System 2. Implement actions from review of Appraisal System 3. Review IRR 4. Implement actions from review of IRR 5. Review AWBM 6. Implement actions from AWBM review | 1. Appraisal system review completed 2. Actions from Appraisal System review implemented 3. IRR review completed 4. Actions from IRR review implemented 5. AWBM review completed 6. AWBM review actions implemented | 1. Sept 2021 2. As agreed following outcome of review 3. Sept 2021 4. As agreed following outcome of review 5. Sept 2021 6. As agreed following outcome of review | 1-6. HR Services | 1 and 2. Appraisal system reviewed and new system - PCDR - introduced in April 2023. 3 and 4. IRR reviewed and augmented to become IRKEP - more explicitly recognising knowledge exchange activities alongside research and reframing the document as a forward-looking plan rather than a backward-facing review. 5 and 6. AWBM was revised and implemented for 2022-23 with enhanced allocations for research, researcher development and ECRs. | 1-6. No further action.
PCDM2 | Support researchers in exploring and preparing for a diversity of careers, for example, through the use of mentors and careers professionals, training, and secondments | 1. Make visiting role appointments to support sector awareness beyond academia so that all Research Institutes and Faculties have visiting appointees. 2. Review pilot ECR mentoring scheme and for effectiveness of career advice | 1. Broad base of expertise available to researchers through visiting appointees 2. ECR Mentoring scheme reviewed in terms of effectiveness of career advice | 1. Sept 2022 2. Nov 2021 | 1. DDsR&I /RIDO 2. RDM | 1. Faculties increasing number of visiting appointees. 2. ECR Mentoring scheme and mentoring scheme more widely being reviewed across ARU; much research mentoring happens informally and formally across faculties in any case. | 1. No further action - now business as usual. 2. Carried forward.
PCDM3 | Allocate a minimum of 10 days pro rata, per year, for their researchers to engage with professional development, supporting researchers to balance the delivery of their research and their own professional development | 1. Ensure line managers have good understanding of Concordat and the defintion of researcher and of development being used by ARU for implementation of Concordat 2.Clarify how 10 days time is included in AWBM allocation. 3. Promote clear understanding that staff development of researchers is not just research specific and can take many forms including opportunities beyond the programme itself and responsive to staff IRRs | 1a. CEDAR survey shows increased awareness of Concordat from 35% to 45% in 2021 with rising %s in subsequent years 1b. Awareness of Research Development Opportunities in CEDAR Survey increased from 48% to 60% by 2023; 2. 50% of staff included by Concordat definition achieving 10 days development 3. Training opportunities relevant to Researcher Development, provided by faculties and HR training progammes to supplement Researcher Development Programme | 1. June 2021 2. June 2023 3. Sept 2023 4. Sept 2022 | 1a. RDM & DDsR&I 1b. RDM & DDsR&I 2. RDM DDsR&I/Chair RDWG 3. RDM, HR Services, DDsR&I | 1a. CEDARS 2021 showed 42% have some understanding of the Concordat to Support the Career Development of Researchers. Outcomes of CEDARS 2023 in this respect awaited. 1b. CEDARS 2021 data showed 69% (n=74) had engaged in or attended activities provided through ARU’s Staff Researcher Development Programme (53% in CEDARS 2020). 83% (n=89) stated they received the monthly Staff Researcher Development newsletter. 2.CEDARS 2021 showed 64% of respondents (n=109) spent up to four days on researcher development in the last year and 16% of respondents spent ten days on training and professional development activities in the last year, Further understanding of what constitutes training and development needs to be further promoted. Significant change made to AWBM to include 100 credits (=100 hours) for full time staff for researcher development, available for all research active staff subject to line management approval; 3. Faculties provide formal and informal training and development programmes. Ongoing liaison with HR services about their provision and opportunities for research focus in training and development sessions. | 1-3. No further action - now business as usual
PCDM4 | Identify opportunities, and allow time (in addition to the 10 days professional development allowance), for their researchers to develop their research identity and broader leadership skills, and provide appropriate credit and recognition for their endeavours | 1. Review Appraisal System 2. Implement actions from review of Appraisal System 3. Review IRR 4. Implement actions from review of IRR 5. Review AWBM 6. Implement actions from AWBM review 7. Review career pathways data for Research Fellow, SRF, PRF and develop Academic Framework for these job roles | 1. Appraisal system review completed 2. Actions from Appraisal System review implemented 3. IRR review completed 4. Actions from IRR review implemented 5. AWBM review completed 6. AWBM review actions implemented 7.Pathways for Research Fellow, SRF, PRF reviewed and Academic Framework for these job roles developed | 1. Sept 2021 2. As agreed following outcome of review 3. Sept 2021 4. As agreed following outcome of review 5. Sept 2021 6. As agreed following outcome of review 7. Sept 2022 | 1-6. HR Services 7. DvC R&I/HR Services | 1 and 2. Appraisal system reviewed and new system - PCDR - introduced in April 2023. 3 and 4. IRR reviewed and augmented to become IRKEP - more explicitly recognising knowledge exchange activities alongside research and reframing the document as a forward-looking plan rather than a backward-facing review. 5 and 6. AWBM was revised and implemented for 2022-23 with enhanced allocations for research, researcher development and ECRs.New appraisal system implemented for 2022-23; and IT system to support it being introduced for 2023-24. 7. Academic Career Framework has aligned promotions pathways for Research Fellow, Senior and Principal Research Fellow roles to Lecturer, Senior Lecturer and Associate Professor. ARU offers investment in travel and subsistence for our researchers to lead, organise and/or participate in local, national and international research workshops, events and conferences. | 1-7. No further action.
PCDM5 | Engage in leadership and management training to enhance their personal effectiveness, and to promote a positive attitude to professional development | 1. Monitor and report on training and development take up by researchers and managers of researchers through Research Development Programme and HR run staff development programmes 2. Monitor and report on take up of Research Leaders training and development 3. Review IRR 4. Implement actions from review of IRR 5. Monitor completion IRRs and establish baselines for completion rates | 1. Annual report on take up of research training and development 2. Annual report on take up of research leadership training and development 3. Review of IRR completed 4. Actions from IRR review implemented 5. Baseline for IRR completion rates established | 1 & 2. Annually in October 3.Sept 2021 4. As agreed following outcome of review 5. Sept 2022 | 1 & 2. RDM & HR Services 3-5 HR Services | 1. RDP reviewed annually including alignment with HR provision, and is now business as usual. 2. Vitae provided a generic research leadership training in December 2022 and January 2023, with a "train the trainer" add-on, reaching more than 70 staff at a variety of career stages across ARU. Working with the "train the trainer" cohort to revise the content to better meet ARU staff needs. 3 and 4. IRR reviewed and augmented to become IRKEP - more explicitly recognising knowledge exchange activities alongside research and reframing the document as a forward-looking plan rather than a backward-facing review. 5. IRKEP process does not allow for systemic monitoring which would provide baselines. IRKEP itself is now robustly tied into AWBM allocation processes, and promoted widely e.g. included in HR new starters checklists to prompt managers' discussions with new staff, the research induction and also through CEDARS (in institutional specific questions). Monitoring IRKEP more directly may be revisited if an alternate approach to provisioning IRKEP is introduced. | 1-5. No further action
Researchers must:
PCDR1 | Take ownership of their career, identifying opportunities to work towards career goals, including engaging in a minimum of 10 days professional development pro rata per year | 1. Ensure researchers have good understanding of Concordat and the defintion of researcher and of development being used by ARU for implementation of Concordat 2.Clarify how 10 days time is included in AWBM allocation. 3. Promote clear understanding that staff development of researchers is not just research specific and can take many forms including opportunities beyond the programme itself and responsive to staff IRRs 4. Review IRR 5. Implement actions from review of IRR | 1a. CEDAR survey shows increased awareness of Concordat from 35% to 45% in 2021 with rising %s in subsequent years 1b. Awareness of Research Development Opportunities in CEDAR Survey increased from 48% to 60% by 2023; 2. 50% of staff included by Concordat definition achieving 10 days development 3. Training opportunities relevant to Researcher Development, provided by faculties and HR training progammes to supplement Researcher Development Programme 4. IRR review completed 5. Actions from IRR review implemented | 1. June 2021 2. June 2023 3. Sept 2023 4. Sept 2021 5. As agreed following outcome of review | 1a. RDM & DDsR&I 1b. RDM & DDsR&I 2. RDM DDsR&I/Chair RDWG 3. RDM, HR Services, DDsR&I 4. & 5. HR Services | 1a. CEDARS 2021 showed 42% have some understanding of the Concordat to Support the Career Development of Researchers. Outcomes of CEDARS 2023 in this respect awaited. 1b. CEDARS 2021 data showed 69% (n=74) had engaged in or attended activities provided through ARU’s Staff Researcher Development Programme (53% in CEDARS 2020). 83% (n=89) stated they received the monthly Staff Researcher Development newsletter. 2. CEDARS 2021 showed 64% of respondents (n=109) spent up to four days on researcher development in the last year and 16% of respondents spent ten days on training and professional development activities in the last year, Further understanding of what constitutes training and development needs to be further promoted. Significant change made to AWBM to include 100 credits (=100 hours) for full time staff for researcher development, available for all research active staff subject to line management approval; 3. Faculties provide formal and informal training and development programmes. Ongoing liaison with HR services about their provision and opportunities for research focus in training and development sessions. 4 and 5. IRR reviewed and augmented to become IRKEP - more explicitly recognising knowledge exchange activities alongside research and reframing the document as a forward-looking plan rather than a backward-facing review. | 1-5. No further action - now business as usual
PCDR2 | Explore and prepare for a range of employment options across different sectors, such as by making use of mentors, careers professionals, training and secondments | 1. Make visiting role appointments to support sector awareness beyond academia so that all Research Institutes and Faculties have visiting appointees. 2. Review pilot ECR mentoring scheme and for effectiveness of career advice | 1. Broad base of expertise available to researchers through visiting appointees 2. ECR Mentoring scheme reviewed in terms of effectiveness of career advice | 1. Sept 2022 2. Nov 2021 | 1. DDsR&I /RIDO 2. RDM | 1. Faculties increasing number of visiting appointees. 2. ECR Mentoring scheme and mentoring scheme more widely being reviewed across ARU; much research mentoring happens informally and formally across faculties in any case. | 1. No further action - now business as usual. 2. Carried forward.
PCDR3 | Maintain an up-to-date professional career development plan and build a portfolio of evidence demonstrating their experience, that can be used to support job applications | 1. Review IRR 2. Implement actions from review of IRR | 1. IRR review completed 2. Actions from IRR review implemented | 1. Sept 2021 2. As agreed following outcome of review | 1 & 2 HR Services | 1 and 2. IRR reviewed and augmented to become IRKEP - more explicitly recognising knowledge exchange activities alongside research and reframing the document as a forward-looking plan rather than a backward-facing review. | 1 and 2. No further action
PCDR4 | Positively engage in career development reviews with their managers | 1. Review Appraisal System 2. Implement actions from review of Appraisal System 3. Review IRR 4. Implement actions from review of IRR | 1. Appraisal system review completed 2. Actions from Appraisal System review implemented 3. IRR review completed 4. Actions from IRR review implemented | 1. Sept 2021 2. As agreed following outcome of review 3. Sept 2021 4. As agreed following outcome of review | 1-4. HR Services | 1, 2. Appraisal system reviewed and new system - PCDR - introduced in April 2023. 3, 4. IRR reviewed and augmented to become IRKEP - more explicitly recognising knowledge exchange activities alongside research and reframing the document as a forward-looking plan rather than a backward-facing review. | 1-4. No further action
PCDR5 | Seek out, and engage with, opportunities to develop their research identity and broader leadership skills | 1. Monitor and report on training and development take up by researchers and managers of researchers through Research Development Programme and HR run staff development programmes 2. Monitor and report on take up of Research Leaders training and development 3. Review IRR 4. Implement actions from review of IRR 5. Monitor completion IRRs and establish baselines for completion rates | 1. Annual report on take up of research training and development 2. Annual report on take up of research leadership training and development 3. Review of IRR completed 4. Actions from IRR review implemented 5. Baseline for IRR completion rates established | 1 & 2. Annually in October 3.Sept 2021 4. As agreed following outcome of review 5. Sept 2022 | 1 & 2. RDM & HR Services 3-5 HR Services | 1. RDP reviewed annually including alignment with HR provision, and is now business as usual. 2. Vitae provided a generic research leadership training in December 2022 and January 2023, with a "train the trainer" add-on, reaching more than 70 staff at a variety of career stages across ARU. Working with the "train the trainer" cohort to revise the content to better meet ARU staff needs. 3 and 4. IRR reviewed and augmented to become IRKEP - more explicitly recognising knowledge exchange activities alongside research and reframing the document as a forward-looking plan rather than a backward-facing review. 5. IRKEP process does not allow for systemic monitoring which would provide baselines. IRKEP itself is now robustly tied into AWBM allocation processes, and promoted widely e.g. included in HR new starters checklists to prompt managers' discussions with new staff, the research induction and also through CEDARS (in institutional specific questions). Monitoring IRKEP more directly may be revisited if an alternate approach to provisioning IRKEP is introduced. | 1-5. No further action
PCDR6 | Consider opportunities to develop their awareness and experience of the wider research system through, for example, knowledge exchange, policy development, public engagement and commercialisation | 1. Ensure RDP includes opportunities for training on KE, Policy Development, public engagement and commercialisation 2. Increase number of compacts with employers 3. Increase collaborative working with employers e.g. KTPs, KEEP+ and consultancy | 1. RDP programme and other training programmes to include training on KE, Policy Development, public engagement and commercialisation 2. Number of university compacts with employers increased 3. Number of KTPs and consultancy projects increaed from 2021 baseline. | 1. Sept 2022 2. Sept 2022 3. May 2023 | 1. RDM& DDsR&I 2. DDsR&I, DvC R&I 3. DDsR&I, RIDO | 1. RDP developed and reviewed annually and commercialisation training etc provided. Consultancy training provided by CODEswitch consultants, four week programme and also six month flagship programme where academics work with businesses to complete a brief. 2. Number of compacts agreed has increased and exceeds University KPI 3. Number of KTP projects not yet increased. All external income generation activities, including research grant bidding, consultancy and contract activity, and KTPs are subject to quarterly External Income Review meetings at Faculty level. | 1-2. No further action 3. Carried forward
* The Concordat defines researchers as individuals whose primary responsibility is to conduct research and who are employed specifically for this purpose by a higher education institution or research institute. The primary audience is research staff, e.g. postdoctoral researchers, research fellows, research assistants. The Concordat encourages institutions to include other groups who actively engage in research as beneficiaries of their Concordat action plan. These could be postgraduate researchers; staff on teaching and research, or teaching contracts; clinicians; professional support staff; technicians.
Key
| ADDS | Assistant Director of the Doctoral School
| DDRI | Deputy Dean, Research and Innovation
| DDS | Dean of the Doctoral School
| DHOS | Deputy Heads of School
| DvCR&I | Deputy Vice-Chancellor, Research and Innovation
| EDI Group | Equality, Diversity and Inclusion Group
| HOS | Heads of school
| HRS | Human Resource Services
| IRR | Individual Research Report
| KEEP+ | Knowledge Exchange and Embed Partnerships
| KTP | Knowledge Transfer Partnerships
| PCDR | Professional Contribution and Development Review
| RDM | Researcher Development Manager
| RIDO | Research and Innovation Development Office
| RDWG | Researcher Development Working Group
| RIWG | Research Integrity Working Group